## Slide 1
SEVENT
The Saudi event marketplace
Pilot target — July 2026
Weekly Progress Report
Where we are at the halfway mark
3 of 6 sprints delivered
~50% of the pilot system built
Supplier side end-to-end · Organizer RFQ flow live
PREPARED 2026-04-16

## Slide 2
WHAT SEVENT IS
One request. One platform. Full audit trail.
Sevent replaces the old "tender" pattern in the Saudi event industry. An organizer sends one request; the platform routes it to the best 3–5 verified suppliers and tracks every step from request through contract. Payments stay off-platform in the pilot — the system records state and generates a legally-consistent contract.
Organizer
Posts events, sends RFQs, compares quotes, accepts one, reviews the supplier afterwards.
Supplier
Gets verified, publishes catalog + pricing, receives RFQs, sends quotes, confirms bookings.
Admin
Verifies suppliers, resolves disputes, has read-only oversight of the entire system.
Public visitor
Browses approved suppliers by category and city — no login required.

## Slide 3
PROGRESS AT A GLANCE
Halfway through a 12-week plan
25
Pilot suppliers seeded (Riyadh + Jeddah)
16
Automated checks passing
SPRINT 1
Foundations & schema
Complete
SPRINT 2
Supplier onboarding
Complete
SPRINT 3
RFQ & auto-match
Complete
SPRINT 4
Pricing & acceptance
Up next
SPRINT 5
Contract & reviews
Planned
SPRINT 6
Harden & ship
Planned
On track for pilot-ready in mid-July 2026 with 20–30 friendly suppliers.

## Slide 4
WHAT'S BEEN DELIVERED
Three sprints, three business capabilities
SPRINT 1 ·
Foundations
All four user roles can sign up and sign in.
Full system data model designed, built, and protected.
Nightly backups + documented restore procedure.
Booking, review, and dispute flows agreed on paper.
SPRINT 2 ·
Supplier side
3-step onboarding wizard for suppliers.
Admin verification queue with approval emails.
Supplier catalog + public profile page live.
Supplier calendar with manual unavailability blocks.
25 pilot suppliers seeded across Riyadh + Jeddah.
SPRINT 3
Organizer & matching
Public browse: category index + city filter.
Organizer dashboard + event creator.
4-step RFQ wizard with response deadline.
Auto-match engine: top 5 suppliers with reasons.
Supplier RFQ inbox with live countdown.

## Slide 5
END-TO-END FLOW
Request to signed contract
Each step is a controlled transition — the platform enforces who can act and when.
1
Event posted
Organizer creates the event with dates, city, guest count, budget.
LIVE
2
RFQ sent
Auto-match picks top 5; organizer confirms shortlist and deadline.
LIVE
3
Quotes received
Each supplier prices a quote; the system snapshots it immutably.
SPRINT 4
4
Acceptance
Organizer accepts one. Slot is locked — no double booking possible.
SPRINT 4
5
Confirmation
Supplier confirms within 48h or the slot auto-releases.
SPRINT 5
6
Contract
PDF generated from the accepted quote. Emailed to both parties.
SPRINT 5
7
Reviews
14-day window after the event. Disputes pause publication.
SPRINT 5
Live today
Next 4 weeks

## Slide 6
BUILT-IN CONTROLS
What the platform guarantees
Rules enforced by the system itself — not by procedure, not by user trust.
Role separation
Organizer cannot reach supplier or admin areas, and vice versa. Enforced on every screen.
No self-approval
Only an admin can change a supplier's verified status. Suppliers cannot flip their own state.
No double-booking
A slot cannot be booked twice. Acceptance transaction locks the slot or fails cleanly.
Immutable quotes
Once a quote is sent it cannot be silently edited. Every version is snapshotted with a hash.
Contract equals quote
Contract PDFs are generated from the accepted quote — they cannot disagree.
Cross-supplier privacy
Supplier A cannot read Supplier B's RFQs, documents, or calendar. Verified by test.
Later to be automated using Nafath and CR
Prevents disagreements
Prevents silent changes. Everything documented
Enforces higher competition and higher Honesty

## Slide 7
TECHNOLOGY CHOICES
Stack at a glance
The one slide with technical content — everything else is system behavior.
PRINCIPLES
Boring tech, strong invariants
Standard tools the market understands. No exotic dependencies.
Money is stored as whole halalas — no decimals, no rounding drift.
Every state change logs who did it and when.
If we ever need managed hosting, the same stack moves in a day.

## Slide 8
WHAT'S NEXT
The path to pilot
Roadmap — next six weeks
4
Pricing, quotes, acceptance
Suppliers send real priced quotes; organizer accepts; slot is locked.
5
Confirm · contract · reviews · disputes
Full loop closed: confirmation → contract PDF → reviews → disputes.
6
Hardening & pilot readiness
Production deploy, backup drill, 2–3 friendly suppliers onboarded for real.
Risks we're watching
Pricing edge cases. If the math surfaces many exceptions, we pause UI and refine the model. Budget built in.
Supplier dry-run late in the plan may reveal usability blockers. Three Sprint 6 days are reserved for polish only.
Self-hosted operations load. Managed hosting is the fallback if ops starts eating time. Not needed so far.
Local environment boot is the only thing blocking an in-browser end-to-end demo today.
Half the pilot is built. Supplier side is end-to-end. Next six weeks add pricing · acceptance · contracts · reviews · deploy.